## 📊 Summary
Ericsson New Site Integration — Multi-Generation Effort Summary
Comparative effort and resource analysis across 2G GSM, 3G WCDMA, 4G LTE, and 5G NR new site integrations on Ericsson equipment. Figures represent typical per-site engineering hours for a standard macro site.
Generation | Technology | Equipment | Total Activities | Total Effort (Hrs) | Max Engineers (Concurrent) | Avg Effort/ Activity (Hrs) | Est. Site Duration (Days) | Complexity | Key Challenge
2G | GSM 900/1800 | BSC G12 + RBS 2000 | 28 | 87 | 3 | 3.1 | 5 | Low-Medium | Frequency planning & interference mgmt
3G | WCDMA/HSPA+ | RNC + Node B RBS 6000 | 30 | 97 | 3 | 3.2 | 6 | Medium | PSC planning, Iub QoS, HSDPA tuning
4G | LTE / LTE-A | eNB AIR Series + EPC | 34 | 111 | 3 | 3.3 | 7 | Medium-High | PCI planning, VoLTE, Carrier Aggregation
5G | NR SA/NSA FR1+FR2 | gNB AIR 6488 + AMF/SMF/UPF | 43 | 167 | 3 | 3.9 | 10 | High | Network slicing, Massive MIMO, mmWave LoS
Phase-wise Effort Breakdown by Generation (Hours)
Phase | 2G | 3G | 4G | 5G
Pre-Integration | 29 | 29 | 35 | 49
Hardware Install | 20 | 21 | 25 | 27
Software Config | 18 | 23 | 23 | 46
Testing & Drivetest | 16 | 20 | 23 | 37
Integration Sign-Off | 4 | 4 | 5 | 8
TOTAL | 87 | 97 | 111 | 167
NOTES & ASSUMPTIONS:
1. Effort hours are per-site estimates for a standard 3-sector macro site; actual hours vary with site complexity.
2. Engineers required = concurrent engineers on-site or on-call during that activity.
3. Duration is calendar days assuming standard 8-hour working day with 2 engineers.
4. 5G mmWave (FR2) activities are optional and apply only where mmWave small cells are deployed.
5. Transmission/backhaul commissioning time is excluded from hardware install (handled by separate transmission team).
6. KPI baseline collection (24 hrs monitoring) is included in effort but runs unattended.

## 🟢 2G GSM
Ericsson 2G New Site Integration — Activity & Effort Matrix
This matrix lists all activities required for Ericsson new site integration, the estimated engineering effort in hours, and the number of engineers required.
Phase | # | Activity | Effort (Hours) | Engineers Req. | Duration (Days) | Primary Role | Notes / Pass Criteria | Cumulative Effort (Hrs) | Status | Phase | Total Hrs | Activities
Pre-Integration | 1 | Site Survey & Civil Assessment | 8 | 2 | 1 | RF / Civil Engineer | Verify tower height, feeder routes, power availability | 8 | Pending | Pre-Integration | 29 | 6
Pre-Integration | 2 | Frequency Plan & ARFCN Allocation | 4 | 1 | 1 | RF Planner | Assign BCCH/TCH ARFCNs; validate C/I ≥ 9 dB | 12 | Pending | Hardware Install | 20 | 4
Pre-Integration | 3 | BSIC / LAC / CI Parameter Design | 3 | 1 | 1 | RF Planner | Define BSS parameters; align with network plan | 15 | Pending | Software Config | 18 | 9
Pre-Integration | 4 | BTS Hardware Delivery & Inspection | 4 | 2 | 1 | Field Engineer | Verify RBS 2000/2206 hardware checklist | 19 | Pending | Testing & Drivetest | 16 | 6
Pre-Integration | 5 | Transport E1 / IP Backhaul Commissioning | 6 | 2 | 1 | Transmission Engineer | Configure E1 or IP link; verify Abis connectivity | 25 | Pending | Integration Sign-Off | 4 | 3
Pre-Integration | 6 | CR / MOP Preparation & Approval | 4 | 1 | 1 | Network Engineer | Change request raised; MOP signed off by NOC | 29 | Pending | TOTAL | 87 | 28
Hardware Install | 7 | BTS Equipment Mounting & Cabling | 8 | 3 | 1 | Field Engineer | Rack mount, power, feeder, antenna alignment | 37 | Pending
Hardware Install | 8 | Antenna & Feeder Installation | 6 | 2 | 1 | Field Engineer | Mount antenna, install feeders, VSWR test | 43 | Pending
Hardware Install | 9 | Power System Commissioning (AC/DC/Battery) | 4 | 2 | 1 | Electrical Engineer | Commission rectifier, battery backup, alarms | 47 | Pending
Hardware Install | 10 | Earth / Grounding Verification | 2 | 1 | 1 | Electrical Engineer | Confirm earthing resistance < 5 Ω | 49 | Pending
Software Config | 11 | BSC Login & Pre-Change Backup | 1 | 1 | 1 | Network Engineer | ALLIP backup; confirm no pre-existing alarms | 50 | Pending
Software Config | 12 | BTS Site Object Creation (RLDEP) | 2 | 1 | 1 | Network Engineer | Create site MO with GPS coordinates | 52 | Pending
Software Config | 13 | Cell Configuration (RLCEL) | 3 | 1 | 1 | Network Engineer | BCCH, BSIC, LAC, CI, band configuration | 55 | Pending
Software Config | 14 | TRX Addition & Frequency Assignment | 2 | 1 | 1 | Network Engineer | RLTRX — one per TRX; verify ARFCN assignment | 57 | Pending
Software Config | 15 | Abis Timeslot Configuration | 2 | 1 | 1 | Transmission Engineer | Map E1 timeslots to TRXs | 59 | Pending
Software Config | 16 | Handover Neighbor List Configuration | 3 | 1 | 1 | RF Engineer | Define intra/inter-BSC neighbors | 62 | Pending
Software Config | 17 | Power Control Parameter Tuning | 2 | 1 | 1 | RF Engineer | Set RXLEV thresholds, MS TX power max | 64 | Pending
Software Config | 18 | Frequency Hopping Setup (if applicable) | 2 | 1 | 1 | RF Engineer | MA list, HSN, MAIO configuration | 66 | Pending
Software Config | 19 | Cell Activation (RLSTC) | 1 | 1 | 1 | Network Engineer | Unlock cell; confirm BCCH broadcast | 67 | Pending
Testing & Drivetest | 20 | BTS Alarm Verification | 1 | 1 | 1 | Network Engineer | Confirm zero Critical/Major alarms | 68 | Pending
Testing & Drivetest | 21 | Call Setup & SDCCH/TCH Loopback Test | 2 | 2 | 1 | RF / Test Engineer | Make test calls; verify MSC connectivity | 70 | Pending
Testing & Drivetest | 22 | Drive Test (DT) — Coverage & Quality | 6 | 2 | 1 | Drive Test Engineer | MapInfo/TEMS; RxLev ≥ -85 dBm target | 76 | Pending
Testing & Drivetest | 23 | Handover Test (Intra & Inter-BSC) | 3 | 2 | 1 | RF Engineer | Verify HO success rate ≥ 97% | 79 | Pending
Testing & Drivetest | 24 | Voice Quality (MOS) Assessment | 2 | 1 | 1 | RF Engineer | MOS ≥ 3.5 target | 81 | Pending
Testing & Drivetest | 25 | KPI Baseline Collection (24 hrs) | 2 | 1 | 1 | Network Engineer | Extract CCR, CSSR, HO success from OSS | 83 | Pending
Integration Sign-Off | 26 | NOC Acceptance & Alarm Clearance | 1 | 1 | 1 | NOC Engineer | NOC confirms site visible, no alarms | 84 | Pending
Integration Sign-Off | 27 | As-Built Documentation Update | 2 | 1 | 1 | Network Engineer | Update NMS records, site database | 86 | Pending
Integration Sign-Off | 28 | Handover to O&M Team | 1 | 1 | 1 | Project Manager | Formal sign-off, RFI issued | 87 | Pending
TOTAL |  | 28 Activities | 87 | 3 |  | Total Site Effort | Total Effort Hours: 87 hrs ¦ Est. Site Days: ~5 days (2 engineers, 8hr shifts) | 87

## 🟣 3G WCDMA
Ericsson 3G New Site Integration — Activity & Effort Matrix
This matrix lists all activities required for Ericsson new site integration, the estimated engineering effort in hours, and the number of engineers required.
Phase | # | Activity | Effort (Hours) | Engineers Req. | Duration (Days) | Primary Role | Notes / Pass Criteria | Cumulative Effort (Hrs) | Status | Phase | Total Hrs | Activities
Pre-Integration | 1 | Site Survey & Radio Environment Assessment | 8 | 2 | 1 | RF / Civil Engineer | CW measurement, interference check, coverage prediction | 8 | Pending | Pre-Integration | 29 | 7
Pre-Integration | 2 | PSC Planning & Allocation | 4 | 1 | 1 | RF Planner | Primary Scrambling Code; validate no PSC collision | 12 | Pending | Hardware Install | 21 | 4
Pre-Integration | 3 | UARFCN / Band Selection | 3 | 1 | 1 | RF Planner | DL/UL UARFCN; Band 1/5/8 selection | 15 | Pending | Software Config | 23 | 9
Pre-Integration | 4 | LAC / RAC / SAC Parameter Design | 2 | 1 | 1 | Core/RF Planner | Routing & Service Area codes per network plan | 17 | Pending | Testing & Drivetest | 20 | 7
Pre-Integration | 5 | Iub Transport (IP/ATM) Design | 4 | 1 | 1 | Transmission Engineer | IP QoS design; DSCP marking plan | 21 | Pending | Integration Sign-Off | 4 | 3
Pre-Integration | 6 | Node B Hardware Delivery & Inspection | 4 | 2 | 1 | Field Engineer | RBS 3000/6000 hardware checklist | 25 | Pending | TOTAL | 97 | 30
Pre-Integration | 7 | CR / MOP Preparation & Approval | 4 | 1 | 1 | Network Engineer | Approved change request; MOP sign-off | 29 | Pending
Hardware Install | 8 | Node B Equipment Mounting & Cabling | 8 | 3 | 1 | Field Engineer | Rack/tower mount; cable dressing | 37 | Pending
Hardware Install | 9 | Antenna & RET Unit Installation | 6 | 2 | 1 | Field Engineer | CPRI cables; RET controller config | 43 | Pending
Hardware Install | 10 | GPS / 1PPS Sync Installation | 3 | 1 | 1 | Field Engineer | GPS unit mounted, cable to Node B | 46 | Pending
Hardware Install | 11 | Power & Grounding Commissioning | 4 | 2 | 1 | Electrical Engineer | Rectifier, battery, earthing < 5 Ω | 50 | Pending
Software Config | 12 | RNC Login & Pre-Change Backup | 1 | 1 | 1 | Network Engineer | RNC config backup; pre-alarm check | 51 | Pending
Software Config | 13 | Node B MO Creation (NodeBFunction) | 2 | 1 | 1 | Network Engineer | Create NodeBFunction with site identity | 53 | Pending
Software Config | 14 | Iub Interface Configuration | 3 | 1 | 1 | Network Engineer | IP/ATM Iub; SCTP/IMA config | 56 | Pending
Software Config | 15 | Node B Software Load & Upgrade | 3 | 1 | 1 | Network Engineer | SW upgrade to approved baseline via ENM | 59 | Pending
Software Config | 16 | UtranCell Configuration (PSC, UARFCN, Power) | 4 | 1 | 1 | RF Engineer | Primary CPICH power, max TX power | 63 | Pending
Software Config | 17 | Iu-CS / Iu-PS Interface Verification | 3 | 1 | 1 | Core/Tx Engineer | SS7/AAL2 or IP Iu-CS; GTP Iu-PS | 66 | Pending
Software Config | 18 | Neighbor Cell List (Intra & Inter-RAT) | 3 | 1 | 1 | RF Engineer | UMTS + GSM neighbors; inter-RAT HO params | 69 | Pending
Software Config | 19 | HSDPA / HSUPA Feature Activation | 3 | 1 | 1 | RF Engineer | HS codes, EUL config; Cat 14/Cat 6 enabling | 72 | Pending
Software Config | 20 | Cell Unlock (administrativeState=UNLOCKED) | 1 | 1 | 1 | Network Engineer | Verify RACH available; Node B synced | 73 | Pending
Testing & Drivetest | 21 | Node B Alarm & Sync Verification | 1 | 1 | 1 | Network Engineer | GPS sync < 1 μs; zero critical alarms | 74 | Pending
Testing & Drivetest | 22 | RRC Connection & AMR Call Test | 2 | 2 | 1 | RF / Test Engineer | CS call + PS data session test | 76 | Pending
Testing & Drivetest | 23 | HSDPA Throughput Test | 3 | 2 | 1 | RF Test Engineer | Target: ≥ 14.4 Mbps DL HSDPA Cat 10 | 79 | Pending
Testing & Drivetest | 24 | Drive Test — Coverage, RSCP, Ec/No | 6 | 2 | 1 | Drive Test Engineer | RSCP ≥ -95 dBm, Ec/No ≥ -12 dB targets | 85 | Pending
Testing & Drivetest | 25 | Soft / Softer Handover Test | 3 | 2 | 1 | RF Engineer | Active set management; HO success ≥ 97% | 88 | Pending
Testing & Drivetest | 26 | Inter-RAT HO Test (3G ↔ 2G) | 3 | 2 | 1 | RF Engineer | Verify CS fallback to GSM | 91 | Pending
Testing & Drivetest | 27 | KPI Baseline (CSSR, HO, RRC SR, TP) | 2 | 1 | 1 | Network Engineer | 24 hr KPI collection from ENIQ-S | 93 | Pending
Integration Sign-Off | 28 | NOC Acceptance & Final Alarm Check | 1 | 1 | 1 | NOC Engineer | Node B visible; no alarms | 94 | Pending
Integration Sign-Off | 29 | As-Built Documentation Update | 2 | 1 | 1 | Network Engineer | OSS-RC, site database, NMS update | 96 | Pending
Integration Sign-Off | 30 | Handover to O&M | 1 | 1 | 1 | Project Manager | RFI signed off | 97 | Pending
TOTAL |  | 30 Activities | 97 | 3 |  | Total Site Effort | Total Effort Hours: 97 hrs ¦ Est. Site Days: ~6 days (2 engineers, 8hr shifts) | 97

## 🟠 4G LTE
Ericsson 4G New Site Integration — Activity & Effort Matrix
This matrix lists all activities required for Ericsson new site integration, the estimated engineering effort in hours, and the number of engineers required.
Phase | # | Activity | Effort (Hours) | Engineers Req. | Duration (Days) | Primary Role | Notes / Pass Criteria | Cumulative Effort (Hrs) | Status | Phase | Total Hrs | Activities
Pre-Integration | 1 | Site Survey & Civil / RF Assessment | 8 | 2 | 1 | RF / Civil Engineer | Coverage prediction, interference scan, civil readiness | 8 | Pending | Pre-Integration | 35 | 8
Pre-Integration | 2 | PCI Planning & Allocation | 4 | 1 | 1 | RF Planner | PCI mod 3 & mod 30 compliance; neighbor validation | 12 | Pending | Hardware Install | 25 | 5
Pre-Integration | 3 | EARFCN & Carrier Bandwidth Selection | 3 | 1 | 1 | RF Planner | Band selection, DL/UL EARFCN, 5/10/20 MHz BW | 15 | Pending | Software Config | 23 | 9
Pre-Integration | 4 | TAC / eNB ID Assignment | 2 | 1 | 1 | Core/RF Planner | Tracking Area Code; eNB ID from NMS | 17 | Pending | Testing & Drivetest | 23 | 8
Pre-Integration | 5 | IP Transport (S1/X2) Design & Provisioning | 6 | 2 | 1 | Transmission Engineer | MPLS/IP transport; DSCP EF for user plane | 23 | Pending | Integration Sign-Off | 5 | 4
Pre-Integration | 6 | Clock Sync (IEEE 1588v2 PTP) Provisioning | 4 | 1 | 1 | Transmission Engineer | PTP grandmaster config; ±50 ns accuracy target | 27 | Pending | TOTAL | 111 | 34
Pre-Integration | 7 | eNB Hardware Delivery & Inspection | 4 | 2 | 1 | Field Engineer | RBS 6000 / AIR unit hardware checklist | 31 | Pending
Pre-Integration | 8 | CR / MOP Preparation & Approval | 4 | 1 | 1 | Network Engineer | ENM-based change request; approved MOP | 35 | Pending
Hardware Install | 9 | eNB / RRU Equipment Mounting & Cabling | 8 | 3 | 1 | Field Engineer | BBU rack, RRU/RRH mounting, CPRI cabling | 43 | Pending
Hardware Install | 10 | Antenna & AIR Unit Installation | 6 | 2 | 1 | Field Engineer | AIR tilt/azimuth per RF plan; torque spec | 49 | Pending
Hardware Install | 11 | CPRI / eCPRI Fiber Commissioning | 4 | 2 | 1 | Field Engineer | Fiber test; CPRI link check | 53 | Pending
Hardware Install | 12 | Power & Grounding Commissioning | 4 | 2 | 1 | Electrical Engineer | Rectifier, battery, earth < 5 Ω | 57 | Pending
Hardware Install | 13 | PTP Grandmaster/Boundary Clock Config | 3 | 1 | 1 | Transmission Engineer | 1588v2 sync chain validation | 60 | Pending
Software Config | 14 | ENM Login & Pre-Change Backup | 1 | 1 | 1 | Network Engineer | Config export; alarm check; zero critical alarms | 61 | Pending
Software Config | 15 | ENodeBFunction MO Creation | 2 | 1 | 1 | Network Engineer | eNB ID, PLMN ID, feature licenses | 63 | Pending
Software Config | 16 | S1-MME Interface Setup (SCTP/NGAP) | 3 | 1 | 1 | Core/Network Engineer | MME IP, SCTP port 36412; TA codes | 66 | Pending
Software Config | 17 | S1-U GTP Endpoint Configuration | 2 | 1 | 1 | Core/Network Engineer | SGW GTPU tunnel endpoint | 68 | Pending
Software Config | 18 | EUtranCellFDD / TDD Configuration | 4 | 1 | 1 | RF Engineer | PCI, EARFCN, BW, TAC, RS power, PRACH config | 72 | Pending
Software Config | 19 | Carrier Aggregation Configuration (LTE-A) | 3 | 1 | 1 | RF Engineer | PCell/SCell, band combination, CA feature activation | 75 | Pending
Software Config | 20 | X2 Setup & ANR / SON Activation | 3 | 1 | 1 | RF Engineer | X2 neighbor setup; ANR, MLB, MRO enable | 78 | Pending
Software Config | 21 | VoLTE / IMS Configuration (QCI-1) | 4 | 1 | 1 | Core/RF Engineer | QCI-1 bearer, SRVCC, IMS APN on PGW | 82 | Pending
Software Config | 22 | Cell Unlock & Initial Access Verification | 1 | 1 | 1 | Network Engineer | Cell UNLOCKED; S1 Setup Response confirmed | 83 | Pending
Testing & Drivetest | 23 | eNB Alarm & Sync Verification | 1 | 1 | 1 | Network Engineer | PTP locked; zero critical alarms | 84 | Pending
Testing & Drivetest | 24 | UE Attach & Default Bearer Test | 2 | 2 | 1 | RF / Test Engineer | LTE attach, default EPS bearer establishment | 86 | Pending
Testing & Drivetest | 25 | Throughput Test (DL/UL FTP/iPerf) | 3 | 2 | 1 | RF Test Engineer | DL ≥ 75 Mbps / UL ≥ 25 Mbps @ RSRP > -85 dBm | 89 | Pending
Testing & Drivetest | 26 | CA Throughput Test | 3 | 2 | 1 | RF Test Engineer | CA DL ≥ 150 Mbps with 2CC | 92 | Pending
Testing & Drivetest | 27 | VoLTE Call Quality Test (MOS, JB) | 3 | 2 | 1 | RF / VoLTE Engineer | MOS ≥ 4.0; jitter < 30 ms; delay < 150 ms | 95 | Pending
Testing & Drivetest | 28 | Drive Test — RSRP, RSRQ, SINR, TP | 6 | 2 | 1 | Drive Test Engineer | RSRP ≥ -100 dBm, SINR ≥ 0 dB targets | 101 | Pending
Testing & Drivetest | 29 | Inter-RAT / Handover Test (4G ↔ 3G/2G) | 3 | 2 | 1 | RF Engineer | CS fallback, SRVCC, LTE handover | 104 | Pending
Testing & Drivetest | 30 | KPI Baseline (CSSR, HO, CA, VoLTE) | 2 | 1 | 1 | Network Engineer | 24 hr KPI from ENM / ENIQ-S | 106 | Pending
Integration Sign-Off | 31 | NOC Acceptance & Alarm Clearance | 1 | 1 | 1 | NOC Engineer | Cell visible in ENM; no alarms | 107 | Pending
Integration Sign-Off | 32 | License Activation Confirmation | 1 | 1 | 1 | Network Engineer | All feature licenses active in ENM | 108 | Pending
Integration Sign-Off | 33 | As-Built Documentation Update | 2 | 1 | 1 | Network Engineer | ENM records, site DB, NMS | 110 | Pending
Integration Sign-Off | 34 | Handover to O&M | 1 | 1 | 1 | Project Manager | RFI signed off | 111 | Pending
TOTAL |  | 34 Activities | 111 | 3 |  | Total Site Effort | Total Effort Hours: 111 hrs ¦ Est. Site Days: ~7 days (2 engineers, 8hr shifts) | 111

## 🔵 5G NR
Ericsson 5G New Site Integration — Activity & Effort Matrix
This matrix lists all activities required for Ericsson new site integration, the estimated engineering effort in hours, and the number of engineers required.
Phase | # | Activity | Effort (Hours) | Engineers Req. | Duration (Days) | Primary Role | Notes / Pass Criteria | Cumulative Effort (Hrs) | Status | Phase | Total Hrs | Activities
Pre-Integration | 1 | Site Survey & RF / Physical Environment | 10 | 2 | 1 | RF / Civil Engineer | LoS assessment (mmWave), coverage model, civil readiness | 10 | Pending | Pre-Integration | 49 | 10
Pre-Integration | 2 | NR PCI Planning (mod 3 & mod 30 compliance) | 4 | 1 | 1 | RF Planner | NR PCI plan; SSB index assignment | 14 | Pending | Hardware Install | 27 | 5
Pre-Integration | 3 | NR ARFCN & Bandwidth Selection (FR1/FR2) | 4 | 1 | 1 | RF Planner | n78/n41/n260; 100/200/400 MHz TDD BW | 18 | Pending | Software Config | 46 | 13
Pre-Integration | 4 | 5G TAC / gNB ID / PLMN Assignment | 2 | 1 | 1 | Core/RF Planner | 5G TAC; gNB ID 24-bit; PLMN from NMS | 20 | Pending | Testing & Drivetest | 37 | 10
Pre-Integration | 5 | Network Slice Design (eMBB/URLLC/mMTC) | 6 | 2 | 1 | Core / Slice Engineer | S-NSSAI, QoS profile, DRB-to-slice mapping | 26 | Pending | Integration Sign-Off | 8 | 5
Pre-Integration | 6 | Fronthaul / Midhaul / Backhaul Design | 6 | 2 | 1 | Transmission Engineer | eCPRI/CPRI fronthaul; MPLS-TP midhaul/backhaul; latency < 100 μs FH | 32 | Pending | TOTAL | 167 | 43
Pre-Integration | 7 | IEEE 1588v2 PTP (±100 ns) Sync Plan | 4 | 1 | 1 | Transmission Engineer | PTP grandmaster redundancy; Class B compliance | 36 | Pending
Pre-Integration | 8 | NSA Option 3x / SA Option 2 Architecture | 4 | 1 | 1 | Core/RF Engineer | Anchor LTE cell selection (NSA); NG interface plan (SA) | 40 | Pending
Pre-Integration | 9 | gNB Hardware Delivery & Inspection | 4 | 2 | 1 | Field Engineer | AIR 6449/6488/3246 checklist | 44 | Pending
Pre-Integration | 10 | CR / MOP Preparation & Approval | 5 | 1 | 1 | Network Engineer | ENM change request; MOP multi-domain approval | 49 | Pending
Hardware Install | 11 | gNB DU / CU Equipment Mounting | 8 | 3 | 1 | Field Engineer | BBU/DU rack mount; CU server install (vRAN) | 57 | Pending
Hardware Install | 12 | AIR / Massive MIMO Unit Installation | 6 | 2 | 1 | Field Engineer | AIR 6488 (64T64R) mount; azimuth/tilt per plan | 63 | Pending
Hardware Install | 13 | eCPRI Fiber Fronthaul Commissioning | 5 | 2 | 1 | Field Engineer | 25GE / 10GE fiber; CPRI bit-rate check | 68 | Pending
Hardware Install | 14 | Power & Grounding Commissioning | 4 | 2 | 1 | Electrical Engineer | High-power rectifier (5G draws ~3kW); earth < 5 Ω | 72 | Pending
Hardware Install | 15 | PTP Grandmaster / Boundary Clock Installation | 4 | 1 | 1 | Transmission Engineer | GPS-disciplined oscillator; ±100 ns sync chain | 76 | Pending
Software Config | 16 | ENM Login & Pre-Change Backup | 1 | 1 | 1 | Network Engineer | Config export; zero critical alarms | 77 | Pending
Software Config | 17 | GNBDUFunction / GNBCUCPFunction MO Creation | 3 | 1 | 1 | Network Engineer | gNB ID, gNBIdLength=24, PLMN, CU-DU split config | 80 | Pending
Software Config | 18 | NG-C Interface Setup (NGAP / AMF) | 4 | 1 | 1 | Core/Network Engineer | AMF IP, port 38412; PLMN/TAC/slice list | 84 | Pending
Software Config | 19 | N3 / N9 (UPF) User Plane Interface Config | 4 | 1 | 1 | Core/Network Engineer | UPF GTP-U endpoint; N3 tunnel setup | 88 | Pending
Software Config | 20 | NRCellDU Configuration (FR1 Sub-6GHz) | 5 | 1 | 1 | RF Engineer | PCI, ARFCN, SCS 30kHz, 100MHz BW, TDD pattern, SSB | 93 | Pending
Software Config | 21 | Massive MIMO Beamforming Configuration | 4 | 1 | 1 | RF Engineer | 64T64R beamforming mode, SSB sweep, MU-MIMO enable | 97 | Pending
Software Config | 22 | NR TDD Frame Structure & PRACH Config | 3 | 1 | 1 | RF Engineer | DDDSUUDDDSUU pattern; PRACH config index 145 | 100 | Pending
Software Config | 23 | NSA EN-DC Configuration (Option 3x) | 5 | 1 | 1 | RF / Core Engineer | MeNB anchor; X2-U extension; SCG bearer setup | 105 | Pending
Software Config | 24 | SA NG Interface & Xn Neighbor Setup | 4 | 1 | 1 | RF Engineer | Xn setup (port 38422); inter-gNB handover params | 109 | Pending
Software Config | 25 | Network Slice Activation (NSSAI Mapping) | 5 | 1 | 1 | Core / Slice Engineer | eMBB/URLLC/mMTC slice; DRB QoS profile activation | 114 | Pending
Software Config | 26 | mmWave FR2 Cell Config (if applicable) | 5 | 2 | 1 | RF Engineer | n260, 400MHz, 120kHz SCS; analog beamforming 64-beam | 119 | Pending
Software Config | 27 | Feature License Activation (ENM) | 2 | 1 | 1 | Network Engineer | Massive MIMO, CA-NR, NR-NSA, NR-SA, URLLC licenses | 121 | Pending
Software Config | 28 | NR Cell Unlock & NG Setup Verification | 1 | 1 | 1 | Network Engineer | NG Setup Response from AMF; cell UNLOCKED | 122 | Pending
Testing & Drivetest | 29 | gNB Alarm & PTP Sync Verification | 1 | 1 | 1 | Network Engineer | PTP ±100 ns locked; zero critical alarms | 123 | Pending
Testing & Drivetest | 30 | 5G NR Registration & PDU Session Test | 3 | 2 | 1 | RF / Test Engineer | 5G SA/NSA registration; default slice PDU session | 126 | Pending
Testing & Drivetest | 31 | eMBB Throughput Test (DL/UL) | 4 | 2 | 1 | RF Test Engineer | DL ≥ 1 Gbps (64T64R); UL ≥ 200 Mbps target | 130 | Pending
Testing & Drivetest | 32 | Carrier Aggregation NR (CA-NR) Test | 4 | 2 | 1 | RF Test Engineer | NR CA; EN-DC split bearer throughput | 134 | Pending
Testing & Drivetest | 33 | URLLC Latency & Reliability Test | 4 | 2 | 1 | RF / Core Test Engineer | E2E latency < 1 ms URLLC; PER < 10^-5 | 138 | Pending
Testing & Drivetest | 34 | Network Slice Isolation Test | 4 | 2 | 1 | Core / Slice Engineer | Verify eMBB/URLLC/mMTC slice QoS isolation | 142 | Pending
Testing & Drivetest | 35 | Beamforming & Coverage Drive Test | 6 | 2 | 1 | Drive Test Engineer | SSRSRP ≥ -100 dBm; beam tracking validation | 148 | Pending
Testing & Drivetest | 36 | NR Handover Test (NR↔NR, NR↔LTE) | 4 | 2 | 1 | RF Engineer | Xn HO; PDCP fallback; SRVCC/MR-DC mobility | 152 | Pending
Testing & Drivetest | 37 | mmWave Beam Management & Blockage Test | 4 | 2 | 1 | RF Test Engineer | Beam failure recovery; sub-6G fallback | 156 | Pending
Testing & Drivetest | 38 | KPI Baseline (NR Reg SR, TP, HO, URLLC) | 3 | 1 | 1 | Network Engineer | 24 hr KPI baseline from ENM / NFMO | 159 | Pending
Integration Sign-Off | 39 | NOC Acceptance & Alarm Clearance | 1 | 1 | 1 | NOC Engineer | gNB & NR cells visible; no alarms | 160 | Pending
Integration Sign-Off | 40 | License & Feature Activation Confirm | 1 | 1 | 1 | Network Engineer | All 5G feature licenses confirmed active | 161 | Pending
Integration Sign-Off | 41 | 5GC Slice SLA Acceptance | 2 | 1 | 1 | Core / Slice Engineer | Slice SLA met per contract KPIs | 163 | Pending
Integration Sign-Off | 42 | As-Built Documentation Update | 3 | 1 | 1 | Network Engineer | ENM, NMS, site DB; vRAN NF catalog updated | 166 | Pending
Integration Sign-Off | 43 | Handover to O&M | 1 | 1 | 1 | Project Manager | RFI signed off; monitoring dashboards live | 167 | Pending
TOTAL |  | 43 Activities | 167 | 3 |  | Total Site Effort | Total Effort Hours: 167 hrs ¦ Est. Site Days: ~10 days (2 engineers, 8hr shifts) | 167